## Cover Page
Clinical Safety Hazard Log - Epilepsy
Programme
Sub-Prog / Project
Prog. Director |  | Status - Draft
Owner |  | Version 0.2
Author | Steve Bentley | Version Date - 10th December 2025
Epilepsy - Clinical Safety Hazard Log
How to Use
| Item | Detail | Example
1 | Harm | Review the harm statements - are these appropriate for your standard? Can you further define these to make more specific for your standard | Progression of wound. Delayed wound healing. Infection of wound. Sepsis requiring hospital admission. Loss of limb. Death.
2 | Existing controls - description | can this text be modified to be more specific for the standard
3 | Existing controls - evidence | document where this control is evidenced - ideally point to a section in a document or a web link.
4 | Initial risk assessment | check that the risk assesment documented is appropriate for the standard
5 | Overall risk assessment | each group of possible causes needs to have an overall risk assessment. This should be the highest risk of all the causes. (NB not the average)
6 | Residual risk | review that the Additional controls are appropriate to the standard
7 | Possible causes appropriate | Each of the causes in the initial hazard log should be reviewed
8 | New causes | As part of the standard development and as part of specific workshops, new specific causes for harm should be identified | The record contains image(s) which a receiving systems cannot display. E.g. wound photograph. The record may or may not contain a verbal description of the image.
9 |  | new causes will need to link to harms and effects - most of the times these will be one of the existing harm/effects.
10 | Update the numbering | after review each cause needs a unique number - add initials to specify the specific project in the format PRSB_xx2a
11 | Add date of addition
12 | Version History | to be maintained
13 | Remove the help | Red text
Copyright © 2018, Health and Social Care Information Centre. NHS Digital is the trading name of the Health and Social Care Information Centre.All Rights Reserved.

## Version History
Amendment History
Version | Date | Amendment History
0.1 | 2025-11-05 | First draft Hazard Log - updated from base standard log
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
Steve Bentley |  | Clinical Safety Officer
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
xxx Project Board
PRSB Assurance Committtee
NHSE Clinical Safety Group
Distribution
NHS England Clinical Safety Personnel
Document Status:
The controlled copy of this document is maintained in the NHS England corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## Hazard Log
|  | Hazard Assessment | [5 empty] | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description | [5 empty] | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[8 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | Previous hazard | Previous Harm | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
PRSB_1a |  | Important information is not available The care professional has to care for the patient without all of the information regarding that patient being available | Inappropriate/delayed or wrong care given to the patient | Harm to the patient – death, major injury/illness through to minor injury/ psychological distress. | An information standard is designed for a specific use case, it is not the design for a complete health care record. If a system only implements the data items included in the information standard then it will not contain a complete record of a patient. |  |  | In guidance documentation accompanying the standard it is made clear that the standard does not define the whole of a clinical record - but part of the record defined by the scope of the standard. | See the standard's documentation | N/A |  | N/A |  | Major | Low | 3 |  | Suppliers/implementers should read the guidance before implementing a standard | [5 empty] | Major | Medium | 3 |  |  | Transferred
PRSB_1b |  |  |  |  | In development of the information standard, critical information for the scenario was not identified and therefore not included in the standard. |  |  | In development of a standard the PRSB goes through extensive consultation with stakeholders including open consultations. | See the standard's documentation | N/A |  | N/A |  | Major | Very Low | 2 |  | Suppliers/implementors are responsible for the safety of the systems being used. Any critical deficits should be identified and reported to PRSB. | [5 empty] | Major | Very Low | 2 |  |  | Open
PRSB_1c |  |  |  |  | When implementing the standard, local implementers do not implement support for all of the data elements in a standard. This may be due to a local decision on the importance of certain data items. |  |  | The standard uses compliance statements - specifying which data items are mandatory, required or optional. Compliance testing process. PRSB develops a minimum viable product specification for each standard.[are these available to all suppliers - free of charge?] | See the standard's documentation | N/A |  | N/A |  | Major | Medium | 3 |  | Suppliers could put their system through the PRSB standards conformance process. Suppliers/implementors are responsible for the safety of the systems being used | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_1d |  |  |  |  | The standards are complex and are misunderstood and therefore not fully implemented. |  |  | PRSB provides implementation guidance and example scenarios to explain the standard. Simulations. ISN description. Presentations - targeted campaigns. Engaging suppliers and clinical staff, patients. | See the standard's documentation | N/A |  | N/A |  | Major | Medium | 3 |  | Suppliers/implementers should read the guidance before implementing a standard | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_1e |  |  |  |  | Healthcare professionals may require detailed rather than summary information set out in the standard e.g. an assessment performed by a local authority may be shown as completed without details of how that decision was made |  |  | PRSB specifies the essential information requirements. Additional information is allowable | See the standard's documentation | N/A |  | N/A |  | Major | Low | 3 |  | Suppliers/implementors are responsible for the safety of the systems being used |  |  |  | organisation should have standard operating procedures to define the information required to be documented. |  | Major | Low | 3 |  |  | Transferred
PRSB_1f |  |  |  |  | The information as defined in the standard is not able to be recorded in the source systems, is recorded in a different way, or not structured. So the information may not be available to the user. |  |  | The PRSB standard defines the information which should be collect and be available to the user. By defining this information systems will be able to be develop to include this information | See the standard's documentation |  |  |  |  | Major | Low | 3 |  | Suppliers/implementors should implement the standard as defined. Suppliers could put their system through the PRSB standards conformance process. | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_1g |  |  |  |  | The user chooses not to view information which is held in multimedia files e.g. About me. |  |  | The standard defines that particular information such as About Me is important to be understood by any care professional involved in a persons care. | About Me standard documentation | Knowledge of about me |  |  |  | Major | Medium | 3 |  | The IT system should be designed to promote important information and provide ready access to it. | [5 empty] | Major | Very Low | 2 |  |  | Open
PRSB_1h |  |  |  |  | Network bandwidth issues prevents or delays large files being shared or viewed. |  |  | When large file are pulled from a database this can lead to delay. Some systems inform the user that this is occurring, rather than just freezing the screen. |  | unknown |  | unknown |  | Major | Low | 3 |  | IT systems should have the ability of notifying users when a large file is downloading. Potentially downloading as a background operation, displaying an alert to users when the file is available. | [5 empty] | Major | Very Low | 2 |  |  | Open
PRSB_1i |  |  |  |  | The end user system does not allow for information to be displayed in accessibility formats. E.g. screen readers, textual rendering of voice files, or video subtitles etc… |  |  | PRSB standards do no specifically design user interface and accessibility | [5 empty] | Major | Medium | 3 |  | Suppliers and implementers must ensure that they comply with mandated accessibility requirements | [5 empty] | Major | Low | 3 |  |  | Transferred
Overall PRSB_1 | [13 empty] | Major | High | 4 | [7 empty] | Major | Low | 3 |  |  | Transferred
PRSB_2a | 2023-01-16 | Poor data quality Information in the care information system is of poor quality. It is incomplete, incorrect, out of date or inconsistent. | Inappropriate/delayed or wrong care given to the patient | Harm to the patient – death, major injury/illness through to minor injury/ psychological distress. | Information in the system is not updated and therefore becomes out dated and potentially contradictory |  |  | All data items included in the standard have associated dates. Information of the same type can be identified using the data structures in the standard. Thus allowing sorting of the data to allow users to interpret the information appropriately | Part of the standard |  |  |  |  | Major | Medium | 3 |  | IT systems should be designed to enable searching and sorting of data elements to enable the viewing of similar information types together. Elements of the record - such as Medications, Allergies and The Problem list should be managed as a single list. |  | User training should include view the information in sortable/searchable lists. Training should include the management of Medications, Allergies, and the Problem list. |  |  |  | Major | Very Low | 2 |  |  | Open
PRSB_2b |  |  |  |  | Lack of context and provenance of data items may make them appear contradictory |  |  | The standards include definition of context and provenance information | Part of the standard |  |  |  |  | Major | Medium | 3 |  | IT systems should maintain the context of data elements where ever possible | [5 empty] | Major | Very Low | 2 |  |  | Open
PRSB_2c |  |  |  |  | Inconsistency in recording of information by different care professionals in different systems. |  |  | The standard aims to minimise this by introduction standard data items | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Providing standardised templates with constrained vocabularies for data entry |  | User training and understanding of the information being recorded. With regular reviews |  |  |  | Major | Very Low | 2 |  |  | Open
PRSB_2d |  |  |  |  | Information recorded against the wrong patient. |  |  | The standard mandates the use of patient identifying information. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Clear display of the patient banner in the clinical system. Similar name alerts. Twin alerts. Alerting the system that more than one patient is open. Clear patient searching mechanisms. Means to correct errors - remove the wrong patient recordings from view |  | Users to check patient against patient present or on phone. Data of birth rather than name. |  |  |  | Major | Low | 3 |  |  | Transferred
PRSB_2e |  |  |  |  | Incorrect information recorded in the patient's record. |  |  | The standard defines repeatable data items which should be familiar to users - decreasing the likelihood | Part of the standard |  |  |  |  | Major | Low | 3 |  | Data validation Clear labels for data items Constrained vocabularies |  | Training to help users understand how data is defined. Feed back audits of data quality |  |  |  | Major | Low | 3 |  |  | Transferred
PRSB_2f |  |  |  |  | Too many mandatory data items may adversely affect data quality by increasing the burden on care professionals. |  |  | PRSB defines data items which are Mandatory/Required/optional for users to populate. Mandatory items are kept to a minimum to deliver safe care. | the standard |  |  |  |  | Major | Low | 3 |  | IT Systems should be designed to auto-populate data fields when ever appropriate. Local implementers can define mandatory fields |  | N/A |  |  |  | Major | Low | 3 |  |  | Transferred
PRSB_2g |  |  |  |  | Using a standards in a use case which is out of scope for the standard. |  |  | The standard clear defines the scope in which is to be used. | Part of the standard |  |  |  |  | Major | Low | 3 |  | IT Systems MUST only implement the standards within areas of scope | [5 empty] | Major | Very Low | 2 |  |  | Open
PRSB_2h |  |  |  |  | Change in information requirement of a standard. E.g. change in statutory requirements, change in policy. |  |  | The PRSB will, wherever possible review its standards in response to a change in the requirements. Updating the standards where appropriate. | Default review period for PRSB standards is 3 years. A maintenance release can be done at any point and can come earlier for a range of reasons including: Critical safety issue, Build up of significant issues in the maintenance log, Significant changes to other PRSB standards and the need to update to keep alignment Significant changes to policy, legal or the environment around the standard impacting the information requirements. PRSB has a support and maintenance service. Users, Suppliers, Policy teams etcc. are able to raise issues to this service. https://theprsb.org/standards/support/ |  |  |  |  | Major | High | 4 | [5 empty] | Handover of the support and maintenance of the Epilepsy Information standard to NHSE |  | Major | Medium | 3 |  |  | Transferred
PRSB_2i |  |  |  |  | Failure to adopt PRSB information standards |  |  | The PRSB takes it's standards through the information standards process (DAPB). The outcome of which is an ISN which mandates the implementation of a standard. PRSB supports the implementation of the standards with implementation guidance. PRSB supports the implementation of standards via the Standards Partnership Scheme and conformance process | see the standards documentation and ISN see https://theprsb.org/partnerscheme/ |  |  |  |  | Major | High | 4 |  | Suppliers should implement PRSB standards. Implementers of IT systems should ensure that the systems they deploy are compliant with PRSB standards. | [5 empty] | Major | Very Low | 2 |  |  | Open
PRSB_2j |  |  |  |  | PRSB standards are updated periodically which may result in changes to the structure or name of sections or elements |  |  | PRSB standards are updated in response to changes in requirements - these changes are clearly recorded and distributed to suppliers and implementors | [5 empty] | Major | Low | 3 |  | suppliers and implementors should update to the latest version of the standard as soon as possible. | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_2k |  |  |  |  | Recording of Assessments including scored assessments. An assessment can be recorded by just the score or result from an assessment or the score and the components which made up that score. If just the score is recorded then there is a risk that the clinician my make assumptions which are incorrect. |  |  | The PRSB standard requires that the score of an assessment and the components which make up that assessment are recorded. | Part of the standard |  |  |  |  | Major | Low | 3 |  | Suppliers should implement PRSB standards. Implementers of IT systems should ensure that the systems they deploy are compliant with PRSB standards. | [5 empty] | Major | Low | 3 |  |  | Transferred
Overall PRSB_2 | [13 empty] | Major | High | 4 | [7 empty] | Major | Low | 3 |  |  | Transferred
PRSB_3a |  | Important data not found or incorrectly interpreted Critical data in the system is hard to locate, missed, misinterpreted or represented incorrectly. | Inappropriate/delayed or wrong care given to the patient | Harm to the patient – death, major injury/illness through to minor injury/ psychological distress. | Unclear which sections should contain specific information e.g. observations and investigations results and therefore it may not be presented where a healthcare professional expects to see it on the screen and what the sections or elements mean e.g. misinterpretation of ' acute' verses repeat prescription medications in system- acute has no end date so the system interprets it as ongoing medication. |  |  | PRSB standards contain descriptions and definitions of the information to be included in specific data elements. Examples and use cases further help to specify these. Specific vocabularies - SNOMED CT or NHS Data dictionary further guide. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Suppliers/implementors are responsible for the safety of the systems being used. System suppliers should use good user inface design principles to help users to find the information they need. | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_3b |  |  |  |  | The data may have been entered into the wrong section of the record by mistake e.g. Reasonable adjustments or allergy information inappropriately included in the About Me, or not correctly populated. |  |  | PRSB standards contain descriptions and definitions of the information to be included in specific data elements. Examples and use cases further help to specify these. Specific vocabularies - SNOMED CT or NHS Data dictionary further guide. | Part of the standard |  |  |  |  | Major | Medium | 3 |  |  |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients |  |  |  | Major | Medium | 3 |  |  | Transferred
PRSB_3c |  |  |  |  | Blank fields may be misinterpreted. There is a lack of clarity over what a blank field signifies (i.e. not recorded, not assessed, not present, etc). |  |  | PRSB guidance states that for mandatory data item, this data item must be included and a null entry included if there is no information. For required or optional data items, if there is no information then these data items should not be recorded. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Suppliers/implementors should implement the standard as defined. |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients. Including the interpretation of missing information. |  |  |  | Major | Low | 3 |  |  | Transferred
PRSB_3d |  |  |  |  | Multiple different systems and data structures, semantics and language and processes across different settings and users which may lead to incorrect interpretation / translation of clinical information |  |  | The standard aims to bring together a common representation of the data across the many systems involved. Including data definitions | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Suppliers/implementors should implement the standard as defined. | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_3e |  |  |  |  | When using diagnosis qualifiers to indicate the certainty of a diagnosis, separation of diagnosis qualifier from diagnosis SNOMED CT code - Data is sent as post-coordinated terms and the receiving system cannot interpret this. |  |  | Specific guidance for this is included in the standards. Suspected diagnoses are to be populated into text. This will potentially be updated when national guidance on the handling of suspected diagnoses is defined and agreed. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Suppliers/implementors should implement the standard as defined. | [5 empty] | Major | Very Low | 2 |  |  | Open
PRSB_3f |  |  |  |  | Data badly presented in the system (GUI). |  |  | The PRSB does not specify system display in it standards | [5 empty] | Major | Medium | 3 |  | Good user interface design is essential for systems supporting the care of patients. |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients |  | N/A |  | Major | Low | 3 |  |  | Transferred
PRSB_3g |  |  |  |  | End user not able to use the system effectively potentially through lack of training. |  |  | The standard does not address user training. | [5 empty] | Major | Medium | 3 |  |  |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients |  |  |  | Major | Low | 3 |  |  | Transferred
PRSB_3h |  |  |  |  | Information not found because of volume of data / information overload - critical data such as significant problems or allergies could be missed. |  |  | The standard produces a familiar picture of the data The standard is designed to contain a small essential dataset for recording. | Part of the standard |  |  |  |  | Major | Low | 3 |  | Good user interface design. Local deployment template design |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients |  |  |  | Major | Low | 3 |  |  | Transferred
PRSB_3i |  |  |  |  | Losing the link to a source document, for example the discharge summary means the context is lost. |  |  | [some words will be provided] | [5 empty] | Major | Very Low | 2 |  | PRSB provenance data support the recording of the where when and who - which can support the linkage of documents/pictures to the record. | [5 empty] | Major | Very Low | 2 |  |  | Open
PRSB_3j |  |  |  |  | Inability to determine where, when and by whom clinical information was recorded means the context is lost |  |  | PRSB provenance data support the recording of the where when and who - which can support the linkage of documents/pictures to the record. | Part of the standard |  |  |  |  | Major | Low | 3 |  | PRSB provenance data support the recording of the where when and who - which can support the linkage of documents/pictures to the record. |  |  |  | systems to record information at point of care by the person giving care. |  | Major | Very Low | 2 |  |  | Open
PRSB_3k |  |  |  |  | Clinician unclear about the purpose of some of the information e.g. in About Me |  |  | The standard has data definitions. The standard links to national policies. Extensive consultation - high level of user recognition and understanding of approach. | Part of the standard |  |  |  |  | Major | Low | 3 |  |  |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients |  |  |  | Major | Very Low | 2 |  |  | Open
PRSB_3l |  |  |  |  | Sections with unstructured data such as 'About Me' or 'problem list' not be easily found in searches and therefore not reviewed in a timely manner |  |  | Text sections such as "About me" can be indexed using Record Artifact SNOMED CT codes. This will allow these section to be retrieved and displayed in IT systems. These are currently not available for all text sections. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Implement the usage of these Record Artifact SNOMED CT codes. Where not available local codes could be used. | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_3m |  |  |  |  | Alerts are not viewed because professionals are unaware where to look for them or are used to pop-ups |  |  | System behaviours not part of the standard. PRSB standards define the content for alerts | [5 empty] | Major | Low | 3 |  | Supplier and implementers of IT systems should ensure that information defined as alerts is clearly displayed to users. |  | users should be trained where to look in their systems to find important information which they should be alerted to. |  | Policy regarding the population and management of important alerts should be developed on organisations. |  | Major | Low | 3 |  |  | Transferred
PRSB_3n |  |  |  |  | Unfamiliar context/terminology to patients/ service users used in populating the information. |  |  | The standard has data definitions. The standard links to national policies. Extensive consultation - high level of user recognition and understanding of approach. | [5 empty] | Major | Low | 3 |  |  |  | Users should be trained to understand the terminology used in their IT systems. Users should be given support in understanding the use of terminology in their systems. |  |  |  | Major | Low | 3 |  |  | Transferred
PRSB_3o |  |  |  |  | Including OTC medication in the same section as prescribed medication and flag not clear or not understood. |  |  | N/A | [5 empty] | Significant | Medium | 2 |  | Suppliers and implementers of systems should ensure that medication obtained "over the counter" is clearly labelled as such |  | User should be trained in the entering of over the counter (OTC) medications. And the identifying of OTC meds in a medication record. |  |  |  | Significant | Low | 2 |  |  | Open
PRSB_3p |  |  |  |  | Different statutory and legal requirements across the four UK countries that may lead to confusion by clinicians about which sections are relevant to the country in which they work. |  |  | N/A | [5 empty] | Significant | Medium | 2 |  | Suppliers and implementers of the standards should ensure that the systems are compliant with the statutory and legal requirements of the country which the system is deployed | [5 empty] | Significant | Low | 2 |  |  | Open
PRSB_3q | 2025-09-16 |  |  |  | Patient/clinician expects to see epilepsy diagnosis in a diagnosis field (under a heading diagnosis). Instead it appears under a heading problem |  |  | The standard defines the information structure of the epilepsy formulation. This decribes the epilepsy problems and diagnoses. | [5 empty] | Major | Medium | 3 |  | Providence information - where the the information has come from. Always show problems and diagnoses together. |  | clear labeling on systems of where information will be found |  |  |  | Major | Low | 3 |  |  | Transferred
PRSB_3r | 2025-09-16 |  |  |  | The model includes the ability to include certainty of a diagnosis (procedure verification status - confirmed/unconfirmed refuted). Some systems will not be able to interpret/display this information correctly. A refuted diagnosis may be recorded as a confirm one. | [8 empty] | Major | Very High | 5 |  | Systems need to be aware that when receiving information from other systems that qualifiers may be present and process this information approapiately |  | Users need to be aware that qualifiers may be used |  | Clinical coders need to be aware that qualifiers may be used |  | Major | Low | 3 |  |  | Transferred
Overall PRSB_3 | [13 empty] | Major | Medium | 5 | [7 empty] | Major | Low | 3 |  |  | Transferred
PRSB_4a |  | Poor data quality - SNOMED CT and other vocabulary content. Information in the care information system is of poor quality. It is incomplete, incorrect, or inconsistent. | Inappropriate/delayed or wrong care given to the patient | Harm to the patient – death, major injury/illness through to minor injury/ psychological distress. | There is not an appropriate code/ term available for the information that needs to be expressed so local codes are developed; |  |  | The standard includes appropriate codes . These have been consulted on so the chances that codes are not available should be reduced. SNOMED CT content can be updated in response to requests for change. | PRSB has a helpdesk to respond to issues with the standards https://theprsb.org/standards/support/ |  |  |  |  | Major | High | 4 |  | PRSB has support and maintenance service to log issues. Local systems running data quality searches. Many systems use standard templates which help users find the appropriate SNOMED CT codes |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients |  |  |  | Major | Medium | 3 |  |  | Transferred
PRSB_4b |  |  |  |  | Process for creating nationally agreed codes is difficult. |  |  | PRSB works closely with the UK Terminology service to ensure that all the terminology content required to implement the standards are available. If required terminology is not available then the standard will not be released for implementation. | [5 empty] | Major | Low | 3 | This would only occur if PRSB was not aware that specific terminology was not available | Suppliers and implementers of standards should assure that the required SNOMED CT codes are available in there systems. As new standards will always require new Terminology content to be created, suppliers and implementers must insure that they have the latest releases of SNOMED CT available. | [5 empty] | Major | Very Low | 2 |  |  | Open
PRSB_4c |  |  |  |  | Some suppliers and care providers systems make extensive use of their own namespace. |  |  | PRSB attempts to include all the SNOMED CT concepts required for suppliers to implement the standards. Thus minimising the use of local codes | Part of the standard |  |  |  |  | Major | Low | 3 |  | Suppliers and implementers of standards should notify the PRSB if there are codes which they require to implement the standards. PRSB can then ensure that these codes are available in the national UK release | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_4d |  |  |  |  | SNOMED CT is dynamic with frequent updates. PRSB may not be up to date with the latest changes to SNOMED CT. |  |  | PRSB will review the SNOMED CT content of standards regularly. Some SNOMED CT vocabularies will be identified as SNOMED CT reference sets - theses will be updated as part of the SNOMED CT release process. | [5 empty] | Major | Medium | 3 |  | Suppliers and implementers of standards should assure; They are able to process concepts which are retired - (i.e. were part of the standard at some time in the past). That they update to the latest version of SNOMED CT as soon as possible. | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_4e |  |  |  |  | Some providers are not updating to the latest versions of SNOMED CT; |  |  | PRSB recommends that suppliers update to the latest version of SNOMED CT as soon as possible | [5 empty] | Major | Medium | 3 |  | Suppliers and implementers of standards should assure that they update their systems to the latest version of SNOMED CT as soon as possible. | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_4f |  |  |  |  | Codes can become inactive and moved or not retained creating difficulty in retrieving historic information. |  |  | PRSB will review the SNOMED CT content of standards regularly. Some SNOMED CT vocabularies will be identified as SNOMED CT reference sets - theses will be updated as part of the SNOMED CT release process. | [5 empty] | Major | Low | 3 |  | Suppliers and implementers of standards should assure that they are able to process SNOMED CT content which becomes inactive in an appropriate manner. | [5 empty] | Major | Low | 3 |  |  | Transferred
PRSB_4g |  |  |  |  | A Value set/reference set belongs to third party who no longer updates it. No identified owner for a value set or reference set. |  |  | The SNOMED CT refset management process identifies owners for reference sets - when reference sets are no longer owned these are then retired. As part of the standards management process the SNOMED CT content is reviewed and updated with active content including reference sets. | [5 empty] | Major | Low | 3 | N/A | [6 empty] | Major | Low | 3 |  |  | Transferred
PRSB_4h | 2025-09-16 |  |  |  | Medications which have been discontinued due to ineffectiveness or not being tolerated (allergies or severe adverse reation would normaly be recorded) not being recorded in the health record. Leading to these medications being represcribed inappropriately. |  |  | The standard defines how this should be acheived | link to place in standard |  |  |  |  | Significant | Low | 2 |  | System suppliers need to develop functionality to record and display that a medication has been tried but discontinued due to ineffectiveness |  | clinicians need to record in systems when medications are discontinued |  |  |  | Significant | Very Low | 1
PRSB_4i | 2025-09-16 |  |  |  | The standard will mandate the new seizure types - released by the ILEA in Feb 2025. Clinicians will be required t use these seizure types when recording information about seizures. A patient record may have the incorrect/outdate seizure types recorded in there record. or have new ones which other clinicians/or the patient may not understand. |  |  | updates the standard when ILAE guidance changes | [5 empty] | Minor | Very High | 3 |  | updating systems inline with the satandard |  | awareness |  | education clinicians/patients |  | Minor | Low | 1
Overall PRSB_4 | [13 empty] | Major | High | 4 | [7 empty] | Major | Medium | 3 |  |  | Transferred
PRSB_5 | 2025-09-16 | Disclosure of information/images without the patients consent or knowledge | Disclosure of information/images with out the patients consent or knowledge | Harm to the patient - psychological distress | The display of patient 'sex' and 'gender' information, in person demographics, which do not match e.g. one states 'male' and the other states 'female'. |  |  | PRSB standards do not define specific access to information requirements | [5 empty] | Considerable | Low | 2 |  | This is an ongoing issue which requires national guidance | [5 empty] | Considerable | Low | 2 |  |  | Open
Note on AE1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Status column would be useful to show where hazards are treated, tolerated, transferred or terminated. Reply: From Martin O in CSCR: The risks transferred are those with residual risk of 3, which is clarified in CSCR summary. If this is how PRSB prefer to present this information that is acceptable to me but I would advise that a column within the hazard log will make it easier for implementers to quickly identify where there are actions they need to take to mitigate risks.
Note on S2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The actions that we expect the suppliers and/or deployers to take when implementing the standard.
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Health IT
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: the practical things that go wrong , or are not available
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The action that the care professional takes which causes harm e.g. wrong or inappropriate treatment given
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The effect that the hazard has on the patient
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: the reasons that the effects happen
Note on Z5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this level of reduction to likelihood justified based on the mitigation? Would make more sense to me to be medium (possible) and transferred to implementers

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | Number of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required

## References
Reference | Description | Version | Doc. No.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16